      - Project Preparation Workshops

      - Hungary-Slovakia-Romania-Ukraine ENPI CBC Programme 2007-2013

      - Uzhgorod, 12-14 December 2011

| Time | Topic | Objective / Content |
| --- | --- | --- |
| 09.30-10.00 | Registration of participants | - Filling in of attendance sheet - Distribution of handout material |
| 10.00-10.30 | Introduction | - Welcoming remarks - Outline of the workshop - Participants expectations |
| 10.30-11.30 | Cross-border problem analysis | Objective To analyse the cross-border problem the project will address and build up the ‘problem tree’ Content - Short presentation on problem analysis and stakeholders analysis - Group work (groups divided by project partnership): - Identifying key problems and constraints of the existing negative situation - Determining the cause-effect relationships - Identifying who’s affected by the problem Handout and resources required - Presentation - Flipchart paper, A6 post-it (yellow), markers |
| 11.30-11.50 | Coffee/Tea Break |  |
| 11.50-12.20 | Objective analysis | Objective To identify potential project objectives and build up the ‘objective tree' Content - Short presentation on objective analysis - Group work: - Formulating solutions from the identified problems - Checking the means-ends hierarchy Handout and resources required - Presentation - Flipchart paper, A6 post-it (green), markers |
| 12.20-13.00 | Strategy analysis | Objective To determine the scope of the project among project partners Content - Short presentation on strategy analysis (taking also into account the call priorities) - Group work: - Analysing identified objectives in relation to feasibility and priority - Selecting the project strategy Handout and resources required - Presentation - A10 post-it (pink) |
| 13.00-14.00 | Lunch |  |
| 14.00-14.30 | Logical Framework Matrix (logframe): intervention logic | Objectives To clarify project intervention logic and the use of the logframe Content - Introduction to logframe definitions and project intervention logic - Group work: - Definition in the logframe of project objectives, results and key activities based on the strategy developed in the morning session - Checking project intervention logic in the logframe Handout and resources required - Presentation - Blank logframe (A3) |
| 14.30-15.00 | Logframe assumptions | Objective To improve the understanding of project assumptions and practice on their definition Content - Short presentation on assumptions - Group work: - Identifying important project pre-conditions and assumptions - Checking whether they are realistic and acceptable - Inserting assumption or reviewing project intervention Handout and resources required - Presentation |
| 15.00-15.40 | Logframe indicators (OVIs) | Objective To improve the understanding of project indicators and practice on their definition Content - Short presentation on indicators and sources and means of verification - Group work: - Defining in the draft logframe indicators of achievement and sources of verification - Checking whether these indicators and sources of verification are available and reliable Handout and resources required - Presentation |
| 15.40-16.00 | Coffee/Tea Break |  |
| 16.00-17.10 | From the logframe to the action plan and project budget | Objectives To enhance understanding and provide practical tips on developing a sound action plan and budget based on project planned activities Content - Presentation on developing an action plan and estimating project budget - Group work: - Practicing developing the action plan on the basis of 1 activity Handout and resources required - Presentation - Blank action plan template |
| 17.10-17.30 | Conclusion | - Review of expectations/evaluation - Conclusions |