## Slide 1: Reminder on “Successful financial reporting”
Hungary Slovakia-Romania-Ukraine ENPI CBC Programme
Follow-up Project Management
and Implementation Training
Uzhgorod 3 & 4 May 2011

## Slide 2: Financial reporting in contract
The narrative and financial reporting is described in article 4 of the Special Conditions of the contract and complemented by:
Article 15.1 of General Conditions (modified by art. 7.2.5 Special Conditions), explaining the conditions for payment claims and the documents to attach
Annex V to contract: model of payment request
Annex VI to contract: model of financial report
Annex VII to contract: model of expenditure verification report (see presentation on expenditure verification)

## Slide 3: Key elements for smooth reporting
Look at the final and interim reports form the beginning. Any information needed for reporting has to start its collection from the beginning
Prepare the project accounting (Beneficiary and partners) with the necessary information for reporting, not just the amount of expenditure
Keep you accounting on an on-going basis; you will not now when you reach the thresholds if you do otherwise.
Agree regular updates of financial information with your partners; reporting in CBC projects is a team work!
Involve your auditors from the beginning; when preparing the payment claim is too late to find a share understanding of the rules

## Slide 4: General information
Nota bene:
The Beneficiary alone is responsible for the correctness of the information in the tables … check the information sent by your partners!!
Forecast budget and follow-up
Requested only for information purposes but very useful also for your project financial monitoring!!
Other
The sheet “sources of funding” has to be included both in interim and final reports
Figures have to be rounded to the nearest euro cent

## Slide 5: Use of exchange rates
Exchange rates:
The project accounting has to be kept in the national currency used by each partner
Interim and final reports include, for each budget line, four columns for each currency: number of units, unit cost in original currency, total cost in original currency and total cost in Euro
Exchange rate to use is the arithmetical average of the one in Inforeuro for the concerned period (sum of the exchange rates of the months of the reporting period divided by the number of months)

## Slide 6: When/how to request the grant payment? (initial pre-financing)
Special Conditions art. 7.2.5 modifies General Conditions art. 15.1:
Payment procedures are set out in Article 4 of the Special Conditions and regardless of the amount of the grant and the duration of the operation the JMA shall pay the grant to the Beneficiary as follows:
An initial pre-financing instalment of 80% of that part of the estimated budget for the first 12 months financed by the Joint Managing Authority as specified in Article 4 of the Special Conditions within 45 days, as from the date of reception by the JMA of signed contract (accompanied by the financial guarantee if required)
Notes: Not coming back on first pre-financing as all got it?

## Slide 7: When/how to request the grant payment? (further pre-financing)
Further pre-financing instalments of the amount specified in Article 4 of the Special Conditions and designed to normally cover the Beneficiary’s financing needs for each twelve month period of implementation of the Action, within 45 days of the Joint Technical Secretariat approving an interim report, accompanied by:
  a request for payment (conforming to the model in Annex V),
  an expenditure verification report under Article 15.6 (conforming to the model in Annex VII),
  a financial guarantee if required under Article 15.7 (conforming to the model in Annex VIII).

## Slide 8: Treshold for further pre-financing
Further pre-financing may only be given if the part of the expenditure actually incurred which is financed by the Joint Managing Authority (by applying the percentage set out in Article 3.2 of the Special Conditions) stands at 70% at least of the previous payment as supported by the corresponding interim report and by an expenditure verification report.
Where the consumption of the previous pre-financing is less than 70%, the amount of the new pre-financing payment shall be reduced by the unused amounts of the previous pre-financing payment.
The total sum of pre-financing under the Contract may not exceed 90% of the amount referred to in Article 3.2 of the Special Conditions.
Notes: Eg if JMA commits to co-finance your project at 90%, should apply 90% - will take an example next slide!

## Slide 9: Example of treshold calculation
Example: Project total budget estimated amount 200.000 €, project over 2 years
1st year budget 100.000 € , 2nd year 100.000 €
Art 3.2 SC: JMA finances 90% of total eligible costs = maximum 180.000 €
1st pre-financing (80% of grant for 1st year budget) = 80%*(90%*100.000) =72.000 €
2nd pre-financing (as in contract SC art. 4.2) = 90.000 €
Forecast final payment (10% grant) = 18.000 €
Treshold to request the 2nd pre-financing of 90.000 €:
72.000 € of 1st pre-financing corresponds to a grant for 80.000 € of eligible project costs (as the JMA finances 90%)
2nd pre-financing can therefore be requested only when at least 70% of 80.000 € are spent, ie when actual expenditures are ≥ 56.000 €
For 56.000 € eligible costs reported, the part of the expenditure financed by the JMA is 90%*56.000= 50.400 €, this stands at 70% of the previous payment.
Calculation: To request the 2nd pre-financing, the Beneficiary must report eligible expenditures ≥ 70%*(advance payment/0,9)
In this example 70%*(72.000/0,9) = 56.000 €
Notes: Eg if JMA commits to co-finance your project at 90%, should apply 90% - will take an example next slide!
2nd pre-financing is already calculated/indicated in contract
Of course maximum amount, will be paid on applying % to real costs

## Slide 10: When/how to request the grant payment? (balance)
The balance within 45 days of the Joint Technical Secretariat approving the final report, accompanied by:
  a request for payment of the balance
  an expenditure verification report
The amount for final payment under art. 4.2 SC is only a forecast. The actual balance will be paid on the basis of the actual eligible expenditures of the project by applying the % of JMA financing, up to the ceiling as specified under art. 3.2 Special Conditions
Follow-up example on a 200.000 € project:
  If the project reports 220.000 €, total grant financing will be 180.000 €; balance payment will be 18.000 €
  If the project reports 180.000 €, total grant financing will be 90%*180.000 = 162.000 €; balance payment will be 0 €!
Notes: If spends more, grant remains at its maximum. If spend less, get the same % applying to less. If even less, recoveries!

## Slide 11: When do partners get the payment?
Art. 4.4 Special Conditions:
The Beneficiary shall transfer the corresponding amounts of the Grant to its partners without delay as from the date of receipt of the instalment of Grant, proportionally to each partner’s contribution to the Action, without making any deduction, retention or further specific charge, and shall submit the proof of transfer to JMA within 10 days.

## Slide 12: Annex VI of contract (Excel file)
The financial part of Annex VI is an Excel sheet with five parts:
General information on how to use it
Forecast budget and follow-up
Interim Report
Sources of funding
Final report
LET’S SEE THEM IN DETAIL!

## Slide 13: Annex V: request for payment
Annex VI with the table has to be an attachment to Annex V, which is the formal request for payment. You will find the model as an annex to your contract