Hungary-Slovakia-Romania-Ukraine ENPI CBC programme 2007-2013

Exercise on eligible costs and supporting documents for a Project event

| Type of eligible costs | Supporting documents |
| --- | --- |
| - Staff costs (of Beneficiary/project partners to prepare and attend the event): - Staff costs are calculated on the basis of monthly timesheets signed by both the employee and the employer specifying the actual time worked on the project - Staff costs are calculated on the basis of the cost per unit rate (monthly, daily or hourly costs) | - Signed timesheets - Work contracts - Details of staff expenditure (broken down into gross salary, social security charges, insurance and other remuneration related costs, and net salary) - Salary statements (pay-slips…) - Proof of payment of other remuneration related costs - Accounting records of Benef./partners |
| - Travel costs (of Benef./partners and/or of participants to the event), including: - Transportation: the most economical (not always cheapeast!) transport to the event for staff and participants. May be paid directly to the service provider (travel agency) or to the person travelling (reimbursement): - Flight (economy class), train, bus - Car /minibus rental or use, fuel for the vehicle - Visa and travel insurance - Subsistence costs: may be paid to the person travelling or to a service provider (travel agency, hotel, restaurant…). May be based on real costs or flat-rate (as per usual practice of Benef./partner) and include either: - Per diems (per overnight stay on mission); OR - Daily allowance (per mission day) + accommodation (hotel expenses) + local travel within the place of mission (bus, metro, tram, taxi); OR - Accommodation (hotel expenses) + meals during mission + local travel within the place of mission (bus, metro, tram, taxi). In any case, the total amount of subsistence costs per overnight stay on mission must not exceed the per diem rates published by the EC at the time of signing the contract: http://ec.europa.eu/europeaid/work/procedures/ implementation/per_diems/index_en.htm | - Invoice from service providers (travel agency, car rental, hotel, restaurant…) including proof of payment - Original transportation tickets (plane, train, bus) and boarding passes (plane) - For fuel and vehicle expenses, a summary list of the distance covered, the average consumption of the vehicle used, fuel costs and maintenance costs - Copy of passport page with visa - Signed receipts for per diem/daily allowances and proof of stay (hotel bills, stamp in passport…) - Signed reimbursement sheets - Mission or event related documents: agenda, list of participants, list of meetings, mission or event report, materials, pictures… - Proof of sound financial management (comparison of transport costs alternatives…) and respect of procurement general principles: best price-quality, fair competition (several offers from travel agencies/hotels, study on market rates…) - Proof of compliance with compulsory procurement procedures and documents related to award procedure (service contract…) - Accounting records of Benef./partners |
| - Equipment and supplies - The purchase or rental of equipment and supplies (new or used) is eligible if it is specifically for the purposes of the project - Must correspond to market rates (value assessment if second-hand) and respect procurement general principles: best price-quality ratio, fair competition - Must respect rule of origin (whatever the amount) - The cost of related services, such as transportation or installation is also eligible | - Equipment displaying reference to EU/programme funding (sticker…) - Invoice, proof of payment and proof of delivery - Proof of origin for any equipment above 5000 EUR - Proof of respect of procurement general principles (several offers, study on market rates…) - Proof of compliance with compulsory procurement procedures and documents related to award procedure (purchase order, contract) - Accounting records of Benef./partners |
| - Publication of material for the event, leaflets, press release… - May be carried out by the Benef./partners or subcontracted - Must respect the visibility requirements | - Samples of all material printed (or forwarded by fax/email) for the event, displaying appropriate visibility on EU/programme funding and disclaimer - Proof of respect of procurement general principles: best price-quality ratio, fair competition (several offers, study on market rates…) - Proof of compliance with compulsory procurement procedures and documents related to award procedure (sercice agreement…) - Invoices and proof of payment - Accounting records of Benef./partners |
| - Interpretation and other costs related to the event (meeting room…) | - Proof of respect of visibility requirements (EU and programme logos…) during the event (photos…) - Signed list of participants - Media coverage of the event (articles…) - Proof of respect of procurement general principles: best price-quality ratio, fair competition (several offers, study on market rates…) - Proof of compliance with compulsory procurement procedures and documents related to award procedure (sercice agreement…) - Invoices and proof of payment - Accounting records of Benef./partners |
| - Administrative costs related to the event Administrative costs are calculated as a fixed % of direct eligible costs (maximum 7%, as indicated in your approved budget) |  |

Always make sure that these costs are included in your project budget and check which budget line you should report these in!

Make sure you appropriately report about this event in your narrative report (indicating the dates and duration of the event, experts involved and participants, expected and achieved results, material printed, etc.)!