###### Operational Monitoring

| Operational Monitoring – key issues |  |
| --- | --- |
| Synopsis of the grant contract | - Usually a summary on one page of the: Project intervention logic: Overall objective/s, Specific objectives, Expected results Target countries/regions Final beneficiaries and/or target groups (if different) Allocated amount including co-financing Time scale - This page should only change when there is an addendum to the contract. |
| Contracting (secondary procurement) | - A summary of the results of contracts (for services, supplies or works) awarded by the Beneficiary and/or Partner/s: Key dates for launching and signing contracts Title of contract Contractor / Supplier Contracted amount Duration of contract - The information accumulates over the lifetime of the project |
| Input / activity/ output monitoring (efficiency) | - Look at the efficiency of project implementation. How well are inputs converted into outputs? Inputs = The resources consumed by the project (staff, supplies, etc.) Are inputs available on time to implement the activities? At the planned costs? Activities = The actions that convert inputs into outputs Is the activity schedule (work plan) available/used by all partners? Are activities implemented as scheduled? Are there any corrective measures, adaptations? Outputs = What is produced by the activities (study, publication, etc.) Are planned outputs delivered? On time? In a logical sequence? Quantity of outputs? Quality? The emphasis of the monitoring is on measurement, not a long description, e.g.: Compare % budget/input use and % time elapsed Compare % budget/input use and % outputs produced |
| Results monitoring (effectiveness and impact) | - Look at the effectiveness of project implementation. How well are results achieved and how well do they contribute to project specific objectives? Results = The immediate effects of the outputs on the target group Are planned results achieved? What is the quality of results/services available? Do the target groups have access to/are they using the results available so far? If not, what factors prevent this? Information for results must be collected from outside the project (survey questionnaire, evaluation forms, etc). Check your logical framework for the source of info for indicators! Impact = Project contribution to the overall objective What impacts are already apparent? What impacts appear likely? Are logical framework targets and indicators likely to be met? To what extent does/will the project have an indirect positive or negative impact (i.e. environment, social, cultural, economic)? Is there coordination/complementarity with other projects/initiatives? |
| Risk monitoring | The risk profile of the project has 4 elements: The identification of potential risks The chance that the risks will materialise The likely effect of the risks The strategy to avoid, counteract, or minimise the damage of the risks Monitoring of adaptation of the project to external conditions: Has project adapted/is able to adapt to ensure benefits for the target groups? If there are unplanned negative effects on the target groups, did/does the project take appropriate measures? Are unplanned positive effects contributing to the results/services? The monitoring report should update the risk analysis and add new risks if relevant – check your logical framework assumptions |
| Sustainability | - Sustainability is built during project implementation so its potential should be monitored regularly Financial/economic viability. Will the services/results be affordable for the target groups at the end of the project? Are the Beneficiaries/Partners able to afford maintenance/replacement of the technologies/services introduced? Is there a financial/economic phase out strategy developed/implemented? Ownership of project by target groups. Are target groups involved in planning/implementation? Will target groups continue to make use of the results or deliver a stream of benefits? Policy support. What is the interaction between the project and relevant policies? Institutional and management capacity. Is the project embedded in institutional structures that will survive after project completion? Will qualified human resources be available to continue to deliver benefits? |
| Horizontal and cross-cutting issues | - Horizontal issues: The respect of EU and programme visibility by all partners (in events, material produced, etc.) - Cross-cutting issues: How does the project mainstream cross-cutting issues such as: Gender equality Environmental sustainability. Is good environmental practice followed in project implementation? Are environmental constraints/opportunities considered? Democracy, good governance. Regular, transparent information and reporting? Organisational adequacy of Beneficiary/Partners (role vs. capacity/mandate)? Participation and ownership by stakeholders? Promotion of human rights (including people with disabilities), children's rights and indigenous peoples Combating HIV/AIDS |
| Good practices | Usually an empty page to record examples of good practice Completion is optional |
| Prognosis for future | Is the project on track? Expectations for next period? Will the planned results be achieved? Are there deviations from the budget or from the payment schedule? |

More information on:

http://www.rcbi.info/usr/2011-10-27-RCBI-Project-Implementation-Manual-final.pdf